The LEAN Communicator’s Approval Process Tool

Assumptions

- This approval process needs to integrate with any calendar or project schedule you maintain. As a result, you may need to adjust this process to fit your already existing calendar or project schedule.

- This approval process assumes you need to look out at least four weeks in advance for planning purposes from two perspectives. First, you need to get commitment from leaders on the content that needs communicating so you can start working with them to define and develop it. And second, you need to get on their calendars for review.

- The RACI tool can help you define the appropriate participants in the approval process. For larger, complex projects that span business units or functions, you may need a different RACI tool.

How to Use This Tool

- Adjust the assumptions to fit your needs.

- Decide the players you need for your RACI.

- Finetune the process/project steps and timing to meet your needs.  If possible, look for steps to streamline or eliminate.

The RACI Tool to Clarify Roles and Implement the Process

This tool—which process gurus, geeks and greenhorns all like to use—helps you keep a handle on who’s doing what and when.

| RACI Tool for Approvals |  |
| --- | --- |
| R | Responsible—the one who gets the work done |
| A | Accountable—the one who has ownership for the outcomes and results |
| C | Consulted—the one[s] who are involved in discussions and decision support |
| I | Informed—the one[s] who are kept abreast of activities |

| Process/Project Step | Team member | Responsibility (R, A, C or I) | Timing |
| --- | --- | --- | --- |
| - Review communications calendar, identify topic requiring communications and confirm the communications sponsor (that is, the individual who will support and champion the issue) | Communications practitioner | R | 4 weeks before anticipated communications released |
| - Contact the content SME (subject matter expert) to gather content | Communications practitioner | R | 4 weeks before anticipated communications released |
| - Provide communications practitioner with content (in as complete a format as possible) and any other pertinent information | SME | A | 3-1/2 weeks before anticipated communications released |
| - Update communications calendar and highlight upcoming communications to sponsor and others who need to know | Communications practitioner | R | 3-1/2 weeks before anticipated communications released |
| - If have concerns, issues or questions, contact communications practitioner and SME | Sponsor | I | 2 days after receiving notification |
| - Prepare first draft of communication material for release for peer review | Communications practitioner | R | 3 weeks before anticipated communications |
| - Provide communications peer review | Another communications practitioner | C | Within 24 hours of receiving copy |
| - Prepare second draft and share with SME (and legal if necessary) | Communications practitioner | R | Within 24 hours of receiving peer review |
| - Provide comments | SME | A | Within 48 hours of receiving peer review |
| - Provide comments (if necessary) | Legal (if needed, depending on subject matter) | C | Within 48 hours of receiving peer review |
| - Prepare third draft for final review and approval | Communications practitioner | R | Within 48 hours of receiving comments |
| - Provide final review | Sponsor | C | Within 48 hours of receiving final draft to review |
| - Prepare for production | Communications practitioner assigned to task | R | 3 days before scheduled release date |
| - Release | Communications practitioner assigned to task | R | As scheduled |